## EffortRawData
Project Name: |  |  |  | You do not need to edit yellow cells! |  |  |  | Entry hints in cells with red corners, just hover over cell.
Project Team Members:
Effort per task in Week ENDING on identified dates
Current Week:
Totals: | 11 |  | 142 | 12 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
Task | Date Added | GitHub Issue | Effort Estimate | Actual Effort | 2021-09-09 | 2021-09-16 | 2021-09-23 | 2021-09-30 | 2021-10-07 | 2021-10-14 | 2021-10-21 | 2021-10-28 | 2021-11-04 | 2021-11-11 | 2021-11-18 | 2021-11-25
Task 1 | 2021-08-27 |  | 8 | 8 | 2021-09-09: 8
Task 2 | 2021-08-28 |  | 6 | 4 | 2021-09-09: 4
Task 3 | 2021-08-29 |  | 6 | 0
Task 4 | 2021-08-30 |  | 6 | 0
Task 5 | 2021-08-31 |  | 18 | 0
Task 6 | 2021-09-01 |  | 18 | 0
Task 7 | 2021-09-02 |  | 18 | 0
Task 8 | 2021-09-03 |  | 18 | 0
Task 9 | 2021-09-04 |  | 18 | 0
Task 10 | 2021-09-05 |  | 18 | 0
Task 11 | 2021-09-06 |  | 8 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on A7: Break big issues into smaller (easier to estimate) "tasks"
Note on B1: Identify Project Name
Note on B2: Identify Project Originator
Note on B4: Update to current "week ending" date
Note on B7: Tracking date added let's us see when we identified specific work items. Good planning means less tasks added as project progresses.
Note on C2: Identify Project Collaborator (if any)
Note on C7: Connects burndown task to github issue!
Note on D7: Best estimate in HOURS of how long to complete task. If having trouble, subdivide task more.
Note on F7: Enter HOURS (half hours can be .5) worked on task #1 in week ending 2/3/21
Note on F8: Enter HOURS worked (half hours can be .5) on task #2 in week ending 2/3/21
Note on G7: Enter HOURS worked (half hours can .5) on task #1 in week ending 2/10/21

## ChartData
DO NOT CHANGE ANYTHING IN THIS SHEET. IT AUTOMATICALLY PULLS DATA FROM THE 'EFFORT_RAW_DATA' SHEET.
Date | Me | Ideal | Forecast | Week
Start | 142 | 142 | 142 | 0
2021-09-09 | 130 | 130.1667 | 130 | 1
2021-09-16 | 130 | 118.3333 | 118 | 2
2021-09-23 | 130 | 106.5 | 106 | 3
2021-09-30 | 130 | 94.6667 | 94 | 4
2021-10-07 | 130 | 82.8333 | 82 | 5
2021-10-14 | 130 | 71 | 70 | 6
2021-10-21 | 130 | 59.1667 | 58 | 7
2021-10-28 | 130 | 47.3333 | 46 | 8
2021-11-04 | 130 | 35.5 | 34 | 9
2021-11-11 | 130 | 23.6667 | 22 | 10
2021-11-18 | 130 | 11.8333 | 10 | 11
2021-11-25 | 130 | 0 | 0 | 12