## Sheet1
This week: | 2020-09-17 |  | Actual Weekly Effort Per Task
Task | Actual Task Effort | Estimated Task Effort | 2020-08-20 | 2020-08-27 | 2020-09-03 | 2020-09-10 | 2020-09-17 | 2020-09-24 | 2020-10-01 | 2020-10-08 | 2020-10-15 | 2020-10-22 | 2020-10-29 | 2020-11-05 | 2020-11-12 | 2020-11-19
Task 1 | 8 | 8 | 2020-08-20: 8
Task 2 | 6 | 6 | 2020-08-27: 6
Task 3 | 6 | 6 | 2020-08-27: 6
Task 4 | 6 | 6 | 2020-08-27: 2; 2020-09-03: 4
Task 5 | 12 | 12 | 2020-09-03: 6; 2020-09-10: 6
Task 6 | 12 | 12 | 2020-09-10: 4; 2020-09-17: 8
Task 7 | 2 | 12 | 2020-09-17: 2
Task 8 | 0 | 18
Task 9 | 0 | 18
Task 10 | 0 | 18
Task 11 | 0 | 26
Task 12 | 0
Task 13 | 0
Task 14 | 0
Task 15 | 0
Task 16 | 0
Task 17 | 0
Task 18 | 0
Task 19 | 0
Task 20 | 0
Task 21 | 0
Task 22 | 0
Task 23 | 0
Task 24 | 0
Task 25 | 0
Task 26 | 0
Task 27 | 0
Task 28 | 0
Task 29 | 0
Task 30 | 0
Task 31 | 0
Task 32 | 0
Task 33 | 0
Task 34 | 0
Task 35 | 0
Task 36 | 0
Task 37 | 0
Task 38 | 0
Task 39 | 0
Task 40 | 0
Task 41 | 0
Task 42 | 0
Planned weekly effort |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Actual Weekly Effort |  |  | 8 | 14 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Date | 2020-08-13 | 2020-08-20 | 2020-08-27 | 2020-09-03 | 2020-09-10 | 2020-09-17 | 2020-09-24 | 2020-10-01 | 2020-10-08 | 2020-10-15 | 2020-10-22 | 2020-10-29 | 2020-11-05 | 2020-11-12 | 2020-11-19
Week number | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Planned Burndown | 142 | 134 | 120 | 110 | 100 | 90 | 80 | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0
Ideal Burndown | 142 | 131.8571 | 121.7143 | 111.5714 | 101.4286 | 91.2857 | 81.1429 | 71 | 60.8571 | 50.7143 | 40.5714 | 30.4286 | 20.2857 | 10.1429 | 4.2633e-14
Actual Burndown | 2020-08-13: 142; 2020-08-20: 134; 2020-08-27: 120; 2020-09-03: 110; 2020-09-10: 100; 2020-09-17: 90
Past Rate | 2020-09-17: 10.4
Future Rate | 2020-09-17: 10
Criteria | 2020-08-13: Points
Upload valid spreadsheet | 2020-08-13: 10
Average at least 9 hours/week | 2020-08-13: 10
Average at most 12 hours/week, or instructor permission | 2020-08-13: 10
Completes all tasks | 2020-08-13: 10
Avoids dramatic increase in effort | 2020-08-13: 10
At least 10 tasks | 2020-08-13: 10
Future tasks should have 3-30 hours of expected effort | 2020-08-13: 10
Current tasks should have 3-12 hours of expected effort | 2020-08-13: 10
Completed tasks should require no more than 12 hours of actual effort | 2020-08-13: 10
No effort reported in future weeks | 2020-08-13: 10
Total | 2020-08-13: 100